## Task List
# | Task ID | Phase | Day | Category | File / Component | Task | Purpose / Why It Matters
1 | P0.01 | Phase 0 | — | Infrastructure | infra/providers.tf | Configure google + google-beta Terraform providers | Pin provider versions so infra is reproducible across environments.
2 | P0.02 | Phase 0 | — | Infrastructure | infra/backend.tf | Define Terraform remote state backend | Allow multi-developer collaboration without state-file conflicts.
3 | P0.03 | Phase 0 | — | Infrastructure | infra/apis.tf | Enable required GCP APIs (Firestore, Storage, Functions, Cloud Build, Secret Manager, IAM, Pub/Sub, Scheduler) | GCP APIs are off by default; explicit enablement avoids 'API not enabled' runtime errors.
4 | P0.04 | Phase 0 | — | Infrastructure | infra/iam.tf | Provision service accounts + IAM bindings for Functions, Cloud Build, Firebase | Least-privilege identities so each component can only touch what it needs.
5 | P0.05 | Phase 0 | — | Infrastructure | infra/firebase.tf | Link GCP project to Firebase project; register web app | Single project surface for both GCP infra and Firebase SDKs.
6 | P0.06 | Phase 0 | — | Infrastructure | infra/firestore.tf | Create Firestore (Native mode) database in us-central1 | Primary persistence layer for users, gallery, subscriptions.
7 | P0.07 | Phase 0 | — | Infrastructure | infra/storage.tf | Provision Cloud Storage bucket for gallery images | Object store for rendered PNGs; URLs handed back to the client.
8 | P0.08 | Phase 0 | — | Infrastructure | infra/auth.tf | Enable Firebase Auth with email/password + email-verification | Identity layer used by all user-facing surfaces.
9 | P0.09 | Phase 0 | — | Infrastructure | infra/secrets.tf | Provision Secret Manager secrets for Gemini, Shopify, Stripe keys | Server-only secret storage; never embedded in client bundle or Git.
10 | P0.10 | Phase 0 | — | Infrastructure | infra/outputs.tf | Emit firebase_web_config and project IDs as outputs | Lets the local .env.local pick up Firebase config without manual lookup.
11 | P0.11 | Phase 0 | — | Infrastructure | infra/variables.tf + terraform.tfvars | Parameterize project ID, region, billing account | Same Terraform code can produce dev / staging / prod stacks.
12 | P0.12 | Phase 0 | — | Security Rules | firestore.rules | Define Firestore security rules (deny client writes to server-only fields) | Defense in depth: even if client SDK is bypassed, server-only fields stay locked.
13 | P0.13 | Phase 0 | — | Security Rules | storage.rules | Define Storage security rules for gallery/{uid}/* paths | Users can only read/write their own gallery objects.
14 | P0.14 | Phase 0 | — | Tooling | firebase.json | Configure Firebase Emulator Suite (Auth 9099, Firestore 8080, Storage 9199, Functions 5001, Pub/Sub 8085, UI 4000) | Local dev mirrors production behavior; CI E2E runs against emulators.
15 | P0.15 | Phase 0 | — | Tooling | firestore.indexes.json | Declare composite indexes for gallery queries | Avoid runtime 'missing index' errors when users browse gallery sorted by createdAt.
16 | P1.01 | Phase 1 | — | Types | types.ts | Define UserAccount, UserTier ('freemium' ¦ 'basic' ¦ 'advanced' ¦ 'designer') | Single source of truth for tier names; used by client + functions.
17 | P1.02 | Phase 1 | — | Shared Constants | shared/tiers.ts | Define RETENTION_DAYS_BY_TIER, QUOTA_BY_TIER, computeExpiresAt, startOfNextMonthUTC | Tier-policy math reused by client UI and server quota checks.
18 | P1.03 | Phase 1 | — | Firebase Client | services/firebaseClient.ts | Initialize Firebase app; conditional emulator wiring via VITE_USE_FIREBASE_EMULATOR | One Firebase instance app-wide; switches between emulator and prod via env flag.
19 | P1.04 | Phase 1 | — | Auth Service | services/authService.ts | signUp / signIn / signOut / sendEmailVerification / sendPasswordReset; password + email validators | Thin wrapper over firebase/auth that the UI consumes.
20 | P1.05 | Phase 1 | — | User Service | services/userService.ts | subscribeToUser(uid, cb) — live Firestore snapshot of users/{uid} | Drives reactive tier/quota/subscription UI across the entire app.
21 | P1.06 | Phase 1 | — | UI | components/Auth.tsx | Sign-in / sign-up screen with validation | Entry point for unauthenticated users.
22 | P1.07 | Phase 1 | — | UI | components/EmailVerificationPending.tsx | Block app until user verifies email; provides resend link | Server-side functions reject unverified users; UI gate matches.
23 | P1.08 | Phase 1 | — | App Shell | App.tsx (auth gate) | 3-state render: loading -> Auth -> EmailVerificationPending -> MainApp | Single render hierarchy ensures no logged-out user ever sees a paid surface.
24 | P1.09 | Phase 1 | — | Cloud Function (Auth Trigger) | functions/src/onUserCreate.ts (initial) | On Firebase Auth user creation, write users/{uid} doc with tier='freemium' defaults | Server-side seeding so the client never has to create its own user doc (rules deny it).
25 | P2.01 | Phase 2 | — | Gallery Service | services/galleryService.ts | subscribeToGallery(uid, cb) — live snapshot of users/{uid}/gallery; saveProductsToImage(uid, imageId, products) | Replace localStorage-backed gallery with Firestore as system of record.
26 | P2.02 | Phase 2 | — | UI | components/Gallery.tsx (Firestore mount) | Render Firestore-backed gallery grid with download/edit/expiry chips | User-visible archive of past renders, tier-aware retention countdown.
27 | P2.03 | Phase 2 | — | UI | components/ExpiryChip.tsx | Color-coded chip showing time-until-deletion per image | Make retention windows tangible so users understand what they get by upgrading.
28 | P2.04 | Phase 2 | — | Storage Layout | Storage convention gallery/{uid}/{imageId}.png | Establish per-user object key prefixing | Trivial scoping in Storage rules; supports per-user quotas and audit.
29 | P2.05 | Phase 2 | — | Security Rules | firestore.rules (gallery subcollection) | Read: own user only. Write: server only (Functions admin SDK). | Prevent client from injecting fake gallery entries that bypass watermarking.
30 | P2.06 | Phase 2 | — | Security Rules | storage.rules (gallery/{uid}/*) | Read own; write server-only | Prevent client from overwriting watermarked output with a clean copy.
31 | P3.01 | Phase 3 | Day 1 | Cloud Function (Callable) | functions/src/proxyRemodel.ts | Callable that consumes base64+instruction, reserves a quota slot, calls Gemini image-edit, watermarks for Freemium, writes Storage object + gallery doc | Move Gemini API key + image generation server-side; client no longer needs Gemini key.
32 | P3.02 | Phase 3 | Day 1 | Cloud Function (Callable) | functions/src/proxyGenerateImage.ts | Text-to-image generation path (currently used by unmounted Generator.tsx) | Symmetry with proxyRemodel; ready to wire if Generator is reactivated.
33 | P3.03 | Phase 3 | Day 1 | Quota Library | functions/src/lib/quota.ts (reserveRenderSlot) | Atomic Firestore transaction: check tier daily+monthly quotas, increment counters, append rolling-24h timestamp | Two concurrent renders cannot both pass the last-slot check.
34 | P3.04 | Phase 3 | Day 1 | Watermark Library | functions/src/lib/watermark.ts | applyWatermark(buffer) — overlay PNG watermark on Freemium output | Free-tier output stays visibly free; removes friction to upgrade.
35 | P3.05 | Phase 3 | Day 1 | Storage Helper | functions/src/lib/storage.ts | uploadAndGetDownloadURL(path, buffer, contentType) | Single upload helper used by every callable that produces an image.
36 | P3.06 | Phase 3 | Day 2 | Cloud Function (Callable) | functions/src/proxyChat.ts | Callable wrapper for Gemini chat (designer assistant) | Move chat API calls server-side too.
37 | P3.07 | Phase 3 | Day 2 | Cloud Function (Callable) | functions/src/proxyGenerateProductList.ts | Callable that turns a rendered image into a shoppable product list (Gemini + Shopify enrichment) | Server-side bridge between AI output and the Shop Look feature.
38 | P3.08 | Phase 3 | Day 2 | Cloud Function (Callable) | functions/src/proxyShopifySearch.ts | Callable for catalog search via Shopify Storefront API | Hides Shopify token; lets product search work without exposing the token client-side.
39 | P3.09 | Phase 3 | Day 2 | Cloud Function (Callable) | functions/src/proxySwapProduct.ts | Callable to suggest a replacement product given an image + current product | Powers the Shop Look 'swap this piece' flow.
40 | P3.10 | Phase 3 | Day 2 | Shopify Library | functions/src/lib/shopify.ts | Storefront API client | Reused by proxyShopifySearch + proxySwapProduct.
41 | P3.11 | Phase 3 | Day 3 | Cloud Function (Firestore Trigger) | functions/src/onGalleryImageFinalize.ts | On gallery image upload, generate thumbnails + write thumbnailPath | Smaller thumbs for gallery grid; full image only loaded on demand.
42 | P3.12 | Phase 3 | Day 3 | Cloud Function (Scheduled) | functions/src/expireOldImages.ts | Pub/Sub scheduled job (daily) deleting images whose expiresAt < now | Enforces retention windows server-side; client cannot tamper with expiry.
43 | P3.13 | Phase 3 | Day 3 | Client Service Refactor | services/geminiService.ts (rewritten) | Replace direct GoogleGenAI client with httpsCallable wrappers | Final removal of any Gemini API key from the client bundle.
44 | P3.14 | Phase 3 | Day 3 | Shared Module Pattern | functions/src/_shared/tiers.ts (build-time copy) | Prebuild script copies shared/tiers.ts into functions/src/_shared/ for the Functions deploy bundle | Single source-of-truth for tier math without symlinks or monorepo tooling.
45 | P3.15 | Phase 3 | Day 3 | Security Rules | firestore.rules (hasAny block for quota fields) | Server-only Firestore rule preventing client from writing monthlyDesignCount, renderTimestamps, totalRenders, tier | Defense in depth: even if a malicious client crafts a Firestore write, rules reject it.
46 | P3.16 | Phase 3 | Day 3 | Secrets Wiring | defineSecret + Secret Manager for gemini-api-key + shopify-token | Each callable declares its required secrets; emulator falls back to .secret.local | Production-grade secret handling; no secret ever in code or env.
47 | P4.01 | Phase 4 | Day 1 | Shared Constants | shared/pricing.ts | STRIPE_PRICE_IDS_BY_TIER, TIER_DISPLAY, TIER_ORDER, compareTiers, getTierFromPriceId, USE_MOCK_STRIPE toggle | Single source of truth for tier presentation and the price-ID <-> tier mapping.
48 | P4.02 | Phase 4 | Day 1 | UI | components/Pricing.tsx | 4-card tier matrix with Most Popular badge, Your Plan badge, upgrade/manage CTAs | Where users decide to pay.
49 | P4.03 | Phase 4 | Day 2 | Cloud Function (Callable) | functions/src/proxyCreateCheckoutSession.ts | Creates Stripe Checkout Session for a given tier; returns redirect URL | Server-side session creation so price IDs cannot be tampered with client-side.
50 | P4.04 | Phase 4 | Day 2 | Cloud Function (Callable) | functions/src/proxyCreateCustomerPortalSession.ts | Creates Stripe Customer Portal session for existing subscribers | Self-serve cancel / payment-method / plan-switch via Stripe's hosted UI.
51 | P4.05 | Phase 4 | Day 2 | Client Service | services/stripeService.ts | createCheckoutSession, createCustomerPortalSession, fireMockWebhookEvent | Client wrappers around the two Stripe callables + dev-mode mock-webhook poster.
52 | P4.06 | Phase 4 | Day 2 | Mock-Mode UI (dev-only) | components/MockCheckout.tsx | Stand-in for Stripe Checkout that simulates a successful card payment | Lets CI E2E run end-to-end without real Stripe; gated behind import.meta.env.DEV.
53 | P4.07 | Phase 4 | Day 2 | Mock-Mode UI (dev-only) | components/MockPortal.tsx | Stand-in for Stripe Customer Portal (cancel / switch) | Lets CI E2E exercise the portal flow without a real Stripe account.
54 | P4.08 | Phase 4 | Day 3 | Cloud Function (HTTP) | functions/src/stripeWebhook.ts | Receives Stripe webhook events (checkout.session.completed, customer.subscription.updated/deleted, invoice.payment_failed); verifies signature; updates users/{uid} | Single source of truth for subscription state; ensures Firestore reflects Stripe.
55 | P4.09 | Phase 4 | Day 3 | Retention Library | functions/src/lib/recomputeExpiry.ts | On tier change, recompute expiresAt for all of user's gallery docs using new tier's RETENTION_DAYS | Downgrades clamp retention windows immediately; upgrades extend them.
56 | P4.10 | Phase 4 | Day 3 | UI Banners | App.tsx (past-due / canceled banners) | Sticky banners shown when subscriptionStatus is 'past_due' or 'canceled' (within currentPeriodEnd) | Surface payment problems so users don't unexpectedly lose tier benefits.
57 | P4.11 | Phase 4 | Day 3 | UI | components/UpgradeSuccess.tsx | Landing screen shown post-Checkout when ?upgrade=success is in URL | Confirms payment + handles the race between Stripe redirect and webhook arrival.
58 | P4.12 | Phase 4 | Day 4 | Cloud Function (Auth Trigger, extended) | functions/src/onUserCreate.ts (Stripe extension) | Provision Stripe Customer at Firebase signup; store metadata.firebaseUid for webhook backref | Removes the 'create-customer-on-first-checkout' race; webhooks always know the uid.
59 | P4.13 | Phase 4 | Day 4 | Webhook Security | stripeWebhook signature verification + dual-mode dispatch | Reject events lacking valid stripe-signature header in prod; allow unsigned in mock mode | Prevents webhook spoofing; preserves CI E2E ergonomics.
60 | P4.14 | Phase 4 | Day 4 | Secrets Wiring | Stripe secrets via defineSecret + GCP Secret Manager | stripe-secret-key + stripe-webhook-secret declared per function; printf '%s' pattern for trailing-newline-free uploads | Same secret discipline as Phase 3; learned to avoid bash <<< heredoc which appends '\n'.
61 | P5.01 | Phase 5 | Day 1 | Quota Service | services/quotaService.ts | getDailyQuotaSnapshot, getMonthlyQuotaSnapshot, isQuotaExhausted; severity ladder ok/warning/critical/exhausted | Pure client-side quota math layer that powers all UX surfaces.
62 | P5.02 | Phase 5 | Day 1 | UI | components/QuotaBadge.tsx | Color-coded daily + monthly chips on Remodeler header; clickable in exhausted state | Live quota visibility so users never get surprised by a hard wall.
63 | P5.03 | Phase 5 | Day 1 | Wiring | components/Remodeler.tsx (QuotaBadge mount) | Replace hard-coded '2/2 transformations' Phase-1 banner with <QuotaBadge> | Remove dead Phase-1 UI; show real numbers.
64 | P5.04 | Phase 5 | Day 1 | Wiring | App.tsx (onNavigateToPricing for Remodeler) | Pass setCurrentMode(PRICING) into Remodeler so exhausted chip can navigate to Membership | Connect the upgrade nudge to the actual destination.
65 | P5.05 | Phase 5 | Day 2 | UI | components/PreRenderWarningModal.tsx | Friendly overlay shown before the user's last allowed daily render; Continue / See plans | One last graceful upgrade opportunity before the hard wall.
66 | P5.06 | Phase 5 | Day 2 | UI | components/QuotaExceededModal.tsx | Replacement for the bare alert() on HttpsError(resource-exhausted); shows counters + Upgrade CTA | Friendly recovery moment instead of a browser alert popup.
67 | P5.07 | Phase 5 | Day 2 | Wiring | components/Remodeler.tsx (modal integration) | handleRemodelClick pre-flight (warning when daily.remaining===1, once-per-UTC-day suppression via localStorage); catch block branches on 'functions/resource-exhausted' | Tie both modals into the render path without changing the happy-case latency.
68 | P5.08 | Phase 5 | Day 3 | Slot Service | services/gallerySlotsService.ts | getSlotLimit (2/5/inf/inf, tied to daily limits); applySlotCap sorts by createdAt desc, slices to top N | Soft visibility cap that nudges upgrade without blocking renders or deleting data.
69 | P5.09 | Phase 5 | Day 3 | UI | components/Gallery.tsx (slot indicator + banner) | Color-coded X / Y slots chip; over-capacity banner with See plans CTA; render visibleImages only | Make slot-cap tangible; older designs are hidden, not deleted.
70 | P5.10 | Phase 5 | Day 3 | Bug Fix | components/Pricing.tsx (Portal routing fix) | Paid-tier users route ALL non-current tier clicks through Customer Portal (not Checkout) | Closes Phase-4 duplicate-subscription bug where Basic->Advanced via Checkout double-billed.
71 | P5.11 | Phase 5 | Day 3 | Wiring | App.tsx (onNavigateToPricing for Gallery) | Pass setCurrentMode(PRICING) into Gallery so over-capacity banner CTA navigates | Same upgrade-nudge wiring pattern as Remodeler.
72 | P5.12 | Phase 5 | Day 4 | Documentation | phase-5-completion-report.md | 12-section completion report mirroring Phase 3/4 style | Audit trail of what shipped, decisions made, deferred items, and Phase 6/7 handoff.

## Summary
Phase | Scope | # Tasks | Status
Phase 0 | Infrastructure (Terraform / GCP) + Security Rules + Emulator config | 15 | Complete
Phase 1 | Auth, user model, email verification, server-seeded user docs | 9 | Complete
Phase 2 | Gallery moved to Firestore + Cloud Storage; retention groundwork | 6 | Complete
Phase 3 | All AI calls moved to Cloud Functions; atomic quota reservation; watermark; retention sweep | 16 | Complete
Phase 4 | Stripe subscriptions: Checkout, Portal, webhooks, tier lifecycle, banners, mock-mode | 14 | Complete
Phase 5 | Tier enforcement UX: quota chips, pre-render warning, exceeded modal, slot caps, Portal routing fix | 12 | Complete
Phase 6 | Admin dashboard with real Firestore aggregations (sign-ups, MRR, churn, DAU/MAU) | — | Not started — optional for launch
Phase 7 | Production cutover: Stripe live keys, App Check, CORS tightening, real watermark PNG, Cloud Monitoring, prod Hosting deploy | — | Not started — critical path
Phase 8 | Cleanup: remove mock layer, delete Generator.tsx + MockCheckout/MockPortal, finalize docs | — | Not started — post-launch